## Sheet1
Draft Short and Long Term (10 year) - Economic Development Strategic Action Plan
Priority | Create an Economic Development Organization |  |  | Responible Party | Resources Needed | Timing
| Action #1 | Create exploratory committee to establish a non-profit Economic Development Organization |  | COC, Cities, County | Tx Economic Dev. Council, | 2018-03-01
| Action #2 | Form an economic development organization and establish formal partnerships and contractual arrangements |  | COC, Cities, County | Staff & Business Reps | 2018-12-01
| Action # 3 | Establish exploratory committee for funding opportunities |  | COC | Staff and Business Reps | 2018-03-01
Priority | Evaluate, Develop and Expand Initiatives of the Cultural Arts District |  |  | Responible Party | Resources Needed | Timing
| Action #1 | Adopt a Cultural Arts District strategic plan. Incorporate these goals into the Economic Development Plan. |  | RCAD, COC, City, County | Staff | Mid-Feb 2018 Planning Session
| Action #2 | Consider combined arts incubator/gallery/housing initiative in the Cultural Arts District/City Center |  | COC, City, County, RCAD, RCA Team | tbd as per CAD Plan
| Action #3 | Activate Cultural Arts District to act as umbrella for coordinated programs and events in the District |  | Cultural Arts District | tbd as per CAD Plan | Feb-Mar 2018
| Action #4 | Consider developing small, frequent cultural and arts programs and events. Ex: music vignettes, family entertainment, funky theme, chalk/digital graffiti |  | Cultural Arts District | $20,000 per year
| Action #5 | Infuse more culture & art projects into the District, Fulton downtown, and gateways. Ex: mural project, public art sculpture, Harvey memorial structure |  | RCAD, RCA | tbd as per CAD & RCAD Plans | On going
* | Action #6 | Facilitate discussions and consider pursuing a shared, multi-purpose facility in the Cultural Arts District/City Center to serve multiple arts, culture, and historic non-profit groups, creating an anchor for the District. |  | All arts/culture, nonprofits; Tourism Council | tbd pending initial discussions, Public Assistance
Priority | Attract Volunteers to Spend Money in Our Community and Help With Recovery |  |  | Responible Party | Resources Needed | Timing
| Action #1 | Develop a "VolunTOURing" program by attracting volunteers to spend money and help with recovery. Build a relationship with volunteers through a positive experience so they will come back |  | Short Term Teams | Staff | 2018-03-01
| Action #2 | Develop packaging (lodging, transportation, activities, tours) |  | Short Term Teams | Staff | 2018-03-01
| Action #3 | Formalize informative tour - venue, transportation, script |  | Short Term Teams | MOU, Attorney, Transportation | 2018-03-01
| Action #4 | Adopt marketing program to attract VolunTOURists. Document what they are doing (images, stories). Stay in touch |  | Short Term Teams | Network List, College Vol. Coordinators | 2018-03-01
Priority | Retain, Support, and Grow Existing Businesses - Organized and New Resources Available in One Spot to Connect Businesses With What They Need |  |  | Responible Party | Resources Needed | Timing
| Action #1 | Conduct business needs assessment - survey, messaging, business walk, database |  | Short Term Teams | Volunteers | Jan-Feb 2018
| Action #2 | Develop business recovery "Toolkit" Program. Assemble business resources based upon assessment (SBDC) |  | Short Term Teams | COC | Jan-Mid Feb '18
* | Action #2A | Pursue a grant program to fund building repair and enhancements, flood proofing, mitigation working capital, and equipment |  | Short Term Teams | Grant Writer | Jan-Mar '18
* | Action #2B | Coordinate with existing nonprofit loan programs (PeopleFund, Lift) and other funding sources (USDA), to secure funding for business building repair and enhancements, floodproofing, working capital, mitigation, and equipment |  | Short Term Teams | COC, Lift, People Fund, SBDC, City | Jan-Mid Feb '18
| Action #3 | Establish a "Resource Hub." Assemble a team for and conduct outreach to businesses |  | Short Term Teams | COC | End Feb 2018
| Action #4 | Provide professional assistance to help cultivate business merchandising, signage, website, and facade |  | Short Term Teams | COC thru Chamber Academy | Mar-Apr 2018
| Action #5 | Establish a program to address recruiting employees back to the community |  | COC | COC | Feb-May 2018
| Action #6 | Consider programs for existing business expansion |  | COC, Cities, County | TBD | 2019
Priority | Pursue Community Quality of Life / Quality of Place / Sense of Place Enhancements |  |  | Responible Party | Resources Needed | Timing
| Action #1 | Develop a master plan to enhance quality of place. Include strategy to minimize code violations; leverage assets such as oak trees, nature etc. |  | Cities, KACB, Pathways | Volunteers, state grant | 2019
| Action #2 | Consider developing city and county demolition programs for dilapidated structures |  | Cities, County | CDBG-DR funds | Fall 2018
| Action #3 | Leverage a partnership with Keep Aransas County Beautiful to execute projects in the master plan and to secure grants |  | Cities, KACB | tbd | 2019
| Action #4 | Pursue partnership with the YMCA to construct a city building and establish YMCA programs. Utilize funding by private donor, city bond, and YMCA. Step 1 is secure a Memorandum of Understand among YMCA, Donor, and City |  | City, Donor, YMCA | Private donation | 2018
| Action #5 | Continue debris removal at water edge, walkways, and roads (fine cleaning) in accordance with FEMA requirements |  | Short Term Teams, Cities, County | KACB, volunteers, Adopt a Highway | Jan-Feb 2018 and monthly
| Action #6 | Rebuild and improve community entrance signs (include community character/branding elements) |  | KACB and Cities | State Keep Tx Beautiful grant | 2019
Priority | Enhance Marketing and Promotion Program to Revitalize Tourism - Targets & Branding |  |  | Responible Party | Resources Needed | Timing
| Action #1 | Communicate we are "open for business" with specific, current information |  | Jeff Hunt of ICF, Short Term Teams | Volunteers, $12,000 | Jan-Feb 2018
| Action #2 | Solidify brand (ecotourism, short getaways, active/sporting getaways) and identify funding to enhance marketing. |  | Jeff Hunt, Short Term Teams | State Hotel/Motel Grant | Apr-June 2018
| Action #3 | Review tourism website and regional tourism websites; make changes/request changes to reflect targeted marketing message |  | COC | Staff | 2018-03-01
| Action #4 | Consider pursuing year round tourism; encourage day trips to counter perceptions that there is nothing to do or no place to stay. |  | Short Term Teams | Staff | Jan-Aug 2018
| Action #5 | Replace venue sign wayfinding program. Inventory all venues and trails, develop, and install wayfinding signage. Ensure design matches the brand |  | Development Council/STT | ICF | Late 2018
Priority | Enhance Marketing and Promotion Program to Revitalize Tourism - Targets & Branding - con't |  |  | Responible Party | Resources Needed | Timing
| Action #6 | Pursue trip packaging and referrals/cross selling |  | Tourism Development Council/STT | 50000 | 2018-08-01
| Action #7 | Link marketing with VolunTOURism program |  | Short Term Teams | Part of VolunTOURism budget | Jan-Feb 2018
| Action #8 | Create "Tourism Army" - build kit for non-tourist businesses and tourist businesses |  | Short Term Teams | 5000 | Jan-Feb 2018
| Action #9 | Encourage the community to support local businesses - Initiate spend local program |  | Short Term Teams | tbd | Mar 2018, Ongoing
| Action #10 | Track hotel availability and actively market this information |  | COC | Staff | Jan-Feb 2018
Priority | Rebuild / Build Local Attractions and Venues |  |  | Responible Party | Resources Needed | Timing
| Action #1 | Conduct community asset inventory |  | Tourism Council | n/a | 2018-02-01
* | Action #2 | Work with non-profit attractions to facilitate rebuilding and seek funding based upon priority and funding availability |  | County, City | Grants | 2018-03-01
| Action #3 | Address pier restorations (private and public) |  | tbd | Grants | Mar-Apr 2018
| Action #4 | Evaluate use and design (possible upgrades and expansion of uses) of buildings in Rockport Beach |  | ACND, City, County Team | n/a | 2018-02-01
| Action #5 | Solicit technical assistance by the Texas Department of Tourism and other outside entities to explore enhancement of existing venues and possibility of new venues (ex: ballfields for tournaments, zipline, expanded winery, brewery, theater, kayaking, paddleboarding) and ecotourism. Seek funding for recommended projects |  | Tourism Council | Tx Dept of Tourism | 2018-02-01
| Action #6 | Create a Design Manual and execute common theming, colors, materials, etc (includes of public facilities, beach facilities, streetscape, landscape, signage, and parks (cities, county, nav) before and while public facilities are being rebuilt and newly built. Use brand created by ICF as basis for theming. |  | ACND, City, County, Tourism Council, RCAD Team, | Engineers, architects, landscape architects | 2018-02-01
Priority | Rebuild / Build Local Attractions and Venues - con't |  |  | Responible Party | Resources Needed | Timing
| Action #7 | Adopt multi-jurisdictional Incentives Policy to attract venues and specialty retail (public & private) |  | Cities, County, Tourism, EDC, ACND | Technical Assistance | Late 2018
| Action #8 | Evaluate updated Retail Leakage report and develop an execution plan |  | New EDC if established | SBDC | 2018-03-01
Priority | Solidify and Advance Rockport Harborfront Boardwalk & Cultural Arts District / City Center to Increase Foot Traffic, Activity, & Spending Through Marketing, Programming, Events, Capital Improvemnets, and Business Recruitment |  |  | Responible Party | Resources Needed | Timing
| Action #1 | Review, update, and consolidate the Heritage District Plan, Cultural Arts District, and Harborfront Plans into one cohesive plan. Include mixed use (housing, retail, office, city hall, county courthouse, cultural arts/heritage facility(s) etc), mixed income. |  | ACND, City, County, COC, non-profits, Tourism Council Team | Planning grant (EDA) | Feb-Mar 2018
| Action #2 | Create a design standards manual to execute the updated District Plan. Establish a clear theme/brand for all improvements (streetscape, signage, banners, landscape, new/redeveloping buildings) in accordance with ICF recommendations. Establish a process to ensure execution by all parties (public and private) |  | ACND, City, County, COC, non-profits, Tourism Council Team | Planning grant (EDA) and or donation, facilitator, landscape artichect | Mar-May 2018
* | Action #3 | Construct the Harbor Boardwalk and Heritage District/Cultural Arts District improvements (infrastructure, landscape, streetscape, parking, signage, etc). Consider seeking grants, loans, and forming a Tax Increment Reinvestment Zone to provide funding |  | ACND, City, County, COC Team | Planning grant, improvement grants, loans, Tax Increment Reinvestment Zone, finance staff, bond counsel | Mar-May 2018
| Action #4 | Develop a business recruitment plan that further the District development and plan. |  | EDC/COC
Priority | Solidify and Advance Rockport Harborfront Boardwalk & Cultural Arts District / City Center to Increase Foot Traffic, Activity, & Spending Through Marketing, Programming, Events, Capital Improvemnets, and Business Recruitment - con't |  |  | Responible Party | Resources Needed | Timing
| Action #5 | Hold a major group cleanup, beautification, and repair event. Minor improvements to public and private infrastructure and buildings - "Extreme District Makeover" |  | Short Term Teams | City, County assistance | Jan-Feb 2018
| Action #6 | Execute beautification projects in accordance with the design standards manual to enhance sense of place |  | Short Term Teams, KACB | City, County assistance | Jan-Mar 2018 & on-going
| Action #7 | Conduct business needs assessment to facilitate more business re-openings; coordinate cohesive downtown business hours and interests |  | Short Term Teams | Staff and volunteers | Jan 2018 & on-going
| Action #8 | Consider new monthly or existing events such as: oysterFest, birding tours, fishing tournaments, harbor stage, auto show, music, drone racing, cruises for Rockport Harbor |  | Short Term Teams, Tourism Council, CAD | 15000 | Jan-on going
| Action #9 | Take interim steps to improve the district. Identify and execute needed infrastucture ie restrooms, parking, relocate sculpture gardens, etc. |  | ACND, City, County, COC Team | Possible Tax Increment Reinvestment Zone and grants | Late 2018
| Action #10 | Link/loop all venues within and outside the District, including downtown Fulton and conference center, via the Aransas Pathways Program. Address disconnects, bottlenecks, and conflicts. Identify additional matching funds for grants to accomplish. |  | Pathways | Grants, TIF | Mar-May 2018
| Action #11 | Support the Navigation District to target market boat traffic in the intercoastal waterway |  | ACND, COC | TIF, other financing | Mar-May 2018
| Action #12 | Anchor the district with city, county, and other public buildings; making this happen starts at the design stage which has already been initiated. Create cohesiveness utilizing the design manual. |  | City, County | Public Assistance, Insurance, Loans | Mar-May 2018
| Action #13 | Address downtown flooding issues |  | City, County | Federal mitigation funding | Mar-May 2018
Priority | Solidify and Advance Fulton Downtown District and Community Center Redevelopment/ Increase Foot Traffic, Activity, & Spending Through Marketing, Programming & Events |  |  | Responible Party | Resources Needed | Timing
| Action #1 | Develop a master plan for Downtown Fulton and establish it as a district |  | City of Fulton, ACND | Texas Planning Assn volunteer facilitators | Jan-Feb 2018
* | Action #2 | Design, identify funding for, and rebuild the Fulton Convention Center (to an even better standard that will increase business). Pursue grant and loan funding options. |  | City of Fulton, ACND | Public Assistance, USDA, mitigation
| Action #3 | Consider common theming the district and coordinating streetscape, landscape, convention center, signage, other improvements (as per ICF brand). Create design manual and supporting team to ensure execution. |  | City of Fulton, ACND team | Design by Tx APA, landscape architect
* | Action #4 | Construct district improvements (infrastructure, landscape, streetscape, parking, signage) and new, small venues (water feature for kids, natural resource/material playground, etc) in accordance with the master plan. |  | City of Fulton, ACND team | USDA, EDA, PA
| Action #5 | Leverage Tourism Marketing Plan to provide updates on available hotels, events, and activities |  | Short Term Teams | $300-$400K annually | 2018-02-01
| Action #6 | Build pride with clean up days |  | Short Term Teams | Volunteers, disposal | 2018-02-01
| Action #7 | Repair/install safety infrastructure including: street lighting, building lighting, safety signs, street signs |  | Short Term Teams | Public Assistance and Mitigation | Jan-Feb 2018
| Action #8 | Update YELP/Trip Advisor/Google - restaurants, hotels, venues - whether businesses are open |  | Short Term Teams | Volunteers | Jan-Feb 2018
| Action #9 | Create promotional maps depicting locations of businesses |  | Short Term Teams | Business printing contribution | Jan-Feb 2018
| Action #10 | Install uniform "open" business signs as per brand |  | Short Term Teams | Individual businesses, Chamber Foundation | Jan-Feb 2018
Priority | Explore Diversifying the Economy with New Target Market(s) |  |  | Responible Party | Resources Needed | Timing
| Action #1 | Work with the Texas Economic Development Corporation to identify new target market industries to stabilize through economic cycles |  | COC, EDC, TEDC | Staff support | Mar - Apr 2018
| Action #2 | Adopt multi-jurisdictional Incentives Policy |  | Cities, County, ACND Team | Staff support | 2018-05-01
Priority | Address "Infrastructure" Necessary to Recruit Alternative Target Industries |  |  | Responible Party | Resources Needed | Timing
Analyze business recruitment Readiness and Take Actions to Address
| Action #1 | Perform Comprehensive Analysis of business site selection factors / considerations and update Economic Development Plan accordingly (see attachment "A" for details)
|  | --Business and operating conditions |  | EDC | EDC Committee
--Geographically variable costs
--Real estate / site
--Business risks
| Action #2 | Establish program to facilitate entrepreneurship |  | EDC | EDC Committee
Address Healthcare Gaps and Needs
| Action #1 | Address lack of regional hospital facilities |  | County | Federal CDBG-DR grants
| Action #2 | Inventory and seek rebuilding of retirement center facilities. |  | City, County, LTR Team | Federal CDBG-DR grants
| Action #3 | Recruit new retirement facility providers in the event there is a long term loss of beds. Explore CDBG-DR funding |  | City, County, LTR Team | Federal CDBG-DR grants
Leverage and Enhance Aransas County Airport for Tourism and Business Diversification
| Action #1 | Update Airport Layout Plan if needed(pursue TXDOT aviation grants) |  | County | TXDOT grant
| Action #2 | Update the Aiport Master Plan if needed(pursue TXDOT aviation grant) |  | County | TXDOT grant
Evaluate Fire Department Needs to Meet New Target Industry Requirements
| Action #1 | Evaluate existing fire department resources and capabilities as it relates to target industry needs |  | EDC, VFD, City, County
Priority | Address "Infrastructure" Necessary to Recruit Alternative Target Industries Con't |  |  | Responible Party | Resources Needed | Timing
Workforce Needs and Development
| Action #1 | Assess workforce skillsets and develop training programs to support target industry |  | EDC, COC | tbd
| Action #2 | Execute Workforce Housing Plan goals and tactics to bring employees back. Recognize that workforce is the #1 factor for primary business locations |  | City, County, LTR Team | tbd
| Action #3 | Develop and execute a marketing strategy for workerforce |  | LTR Team, EDC, COC
| Action #4 | Hold a combined regional housing and jobs fair (loans, credit counseling etc) |  | COC,HUD, LTR Team | tbd
Address Where Companies Will Locate ie Business Parks, Other Sites, and Buildings
| Action #1 | Consider purchasing property for a business park or consider landbanking of city or county owned property for a business park |  | EDC, City, County Team | tbd
| Action #2 | Consider constructing infrastructure to serve the park |  | EDC, City, County Team | Capital Fund Grant
| Action #3 | As a new business is identified, work with Texas Dept of Agriculture on a Texas Capital Fund grant or EDA grant to extend infrastructure/utilities into the business park |  | EDC, City, County Team | Capital Fund Grant
| Action #4 | Perform a building inventory and make recommendation to address deficits |  | EDC | tbd
Pursue Transportation Enhancements to Support Tourism and Business Diversification
| Action #1 | Review area transportation thoroughfares and pursue local/state improvements; adopt Transportation Plan |  | EDC, City, County, COG | Staff
| Action #2 | Address the intersection at Broadway and Business 35. |  | City | tbd
| Action #3 | Continue to pursue multi-modal transporation |  | Aransas Pathways | Grants